## Gantchart
GANTT CHART					Smartsheet Tip ➜					A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.

Kitchen Automation					COLLEGE NAME					A.P Shah Institute of Tech.
Prof. Jaya D. Gupta					DATE					31/10/19

WBS NUMBER	TASK TITLE	TASK OWNER	START DATE	DUE DATE	DURATION(Weeks)	PCT OF TASK COMPLETE	PHASE ONE					PHASE TWO					PHASE THREE					PHASE FOUR
				WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5					WEEK 6					WEEK 7					WEEK 8					WEEK 9					WEEK 10					WEEK 11					WEEK 12
				M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
1	Project Conception and Initiation
1.1	Research paper search	S,A,R	10/7/19	25/7/19	3	100%
1.1.1	Research paper finalization	S	25/7/19	26/7/19	3	100%
1.2	Project Title	S,A,R	26/7/19	2/8/19	3	100%
1.3	Abstract	S	23/8/19	6/9/19	1	100%
1.4	Objectives	R	23/8/19	6/9/19	1	100%
1.5	Literature Review	A	23/8/19	6/9/19	1	100%
1.6	Problem Definition	S	23/3/18	6/9/19	1	100%
1.7	Scope	S	23/8/19	6/9/19	1	100%
1.8	Technology stack	S	23/8/19	6/9/19	1	100%
1.9	Benefits for environment	A,R	23/8/19	6/9/19	1	100%
1.1	Benefits for society	A,R	23/8/19	6/9/19	1	100%
1.11	Applications	A,R	23/8/19	6/9/19	1	100%
2	Project Design
2.1	Proposed System	S	20/10/19	30/9/19	1	100%
2.2	Design(Flow Of Modules)	R,S	20/9/19	30/9/19	1	100%
2.3	Activity Diagram	A,S	20/9/19	30/9/19	1	70%
2.4	Use Case Diagram	A	20/9/19	30/9/19	1	60%
2.5	Description Of Use Case	R	20/9/19	30/9/19	1	75%
2.6	Modules	S,A,R	20/9/19	30/9/19	1
2.6.1	Module-1	S,R	20/9/19	30/9/19	1
2.6.2	Module-2	S,R	20/9/19	30/9/19	1
2.6.3	Module-3	S,R	20/9/19	30/9/19	1
2.6.4	Module-4	S,R	20/9/19	30/9/19	1
2.7	Preparation Of Report	S	20/9/19	30/9/19	1
3	Project Implementation
3.1	Module-1				0	0%
3.2	Module-2				0	0%
3.3	Module-3				0	0%
3.4	Module-4				0	0%
4	Testing
4.1	Design of Test Cases				0	0%
4.2	Testing				0	0%
5	Results and Analysis
5.1	Analysis Of Results				0	0%
5.2	Graphical Representation				0	0%
5.3	Report Preparation